## Sheet1
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17
1 | Define a Problem
Gather Information
Problem Statement / Definition for Design Brief
2 | Brainstorm
Generate and Record Ideas
Make Sketches
Create a List of Ideas
3 | Research and Generate Ideas
Market Research
Conduct Surveys
4 | Identify Criteria and Specify Constraints
Identify what solution should do and to what degree
Identify Constraints
Draft Design Brief
5 | Explore Possibilities | bar: Day 4
Further Development of Brainstorming Ideas | bar: Day 4
Explore alternate ideas | bar: Day 4
6 | Select an Approach | bar: Day 4
Review brainstormed information | bar: Day 4
Narow down ideas via vote or decision matrix | bar: Day 4
Decide on final idea--get approved by intstructor | bar: Day 4
7 | Develop a Design Proposal | bar: Day 4 to Day 5
Annotated Sketches | bar: Day 4 to Day 5
Decide material types and manufacturing methods | bar: Day 4 to Day 5
Generated detailed sketches through computer models | bar: Day 4 to Day 8
Produce working drawings | bar: Day 4 to Day 11
8 | Make a Model or Prototypes | bar: Day 4 to Day 13
Make models | bar: Day 4 to Day 13
Construct Prototype from Working Drawings | bar: Day 4 to Day 13
9 | Test and Evaluate Design Using Specifications | bar: Day 4 to Day 14
Design experiments & test prototype | bar: Day 4 to Day 14
Gather Performance Data | bar: Day 4 to Day 14
Conduct Formal Critique | bar: Day 4 to Day 14
10 | Refine the Design | bar: Day 4 to Day 15
Make design changes | bar: Day 4 to Day 15
Modify prototype until performance is consistant | bar: Day 4 to Day 15
Update Documentation | bar: Day 4 to Day 15
Receive user critique | bar: Day 4 to Day 15
11 | Create or Make Solution | bar: Day 4 to Day 16
Determine custom/mass production | bar: Day 4 to Day 16
Consider Packaging | bar: Day 4 to Day 16
12 | Communicate Processes and Results | bar: Day 4 to Day 17
Communicate final solution via report, PowerPoint | bar: Day 4 to Day 17
Market the Product | bar: Day 4 to Day 17
Distribute | bar: Day 4 to Day 17
Not Started
In Progress
Complete